## Show Prep
Chalke Valley Festival — Art Show Prep Checklist
Nic Ledger ¦ Show: June 2026 ¦ Generated 28 April 2026
Category | # | Task | Detail / Notes | Deadline | Status | Est. Cost (£)
Paintings — Where We Are From | 1 | Final pass on each canvas | Decide which pieces are 'show-ready'; finish weakest areas first. | By 15 May | Not started
Paintings — Where We Are From | 2 | Sign & date each piece | Consistent placement; dated to year of completion. | By 22 May | Not started
Paintings — Where We Are From | 3 | Varnish | Allow drying time — minimum 6 weeks oil cure before retouch varnish; check each canvas. | By 25 May | Not started | 30
Paintings — Where We Are From | 4 | Frame / float-mount | Decide framed vs unframed; keep style consistent across the series. | By 1 June | Not started | 400
Paintings — Where We Are From | 5 | High-res photography | For prints, archive, website, press. Daylight or polarised lighting; colour-checker card. | By 10 May | Not started
Paintings — Where We Are From | 6 | Title cards & artist statement | One short paragraph per piece; one overarching series statement. | By 25 May | Not started | 20
Paintings — Where We Are From | 7 | Pricing decisions | Set originals pricing; record on inventory sheet. | By 25 May | Not started
Religious Icon Paintings | 1 | Complete each icon | List which are show-bound; finish in priority order. | By 20 May | Not started
Religious Icon Paintings | 2 | Gilding / final detailing | Burnishing, halo work, edge treatment. | By 25 May | Not started | 50
Religious Icon Paintings | 3 | Seal / varnish appropriately | Different cure regime to the oils — note medium used. | By 28 May | Not started | 20
Religious Icon Paintings | 4 | Frame or present on board edges | Decide whether icons are framed or shown raw on their boards. | By 1 June | Not started | 200
Religious Icon Paintings | 5 | Photograph for prints & archive | Same shoot as the main series if possible. | By 10 May | Not started
Religious Icon Paintings | 6 | Pricing & provenance notes | Brief note on tradition / iconographic source for each piece. | By 25 May | Not started
Prints | 1 | Choose printer | Compare giclée providers (theprintspace, Loxley, Whitewall, local); request sample. | By 5 May | Not started
Prints | 2 | Decide print sizes & editions | e.g. A4 open edition, A3 limited edition of 50; signed & numbered. | By 8 May | Not started
Prints | 3 | Order test prints | Always test before bulk run — colour, paper, weight. | By 12 May | Not started | 60
Prints | 4 | Order full print run | Allow 10 working days lead time; build in a buffer. | By 22 May | Not started | 600
Prints | 5 | Sign & number limited editions | Pencil; consistent placement; certificate of authenticity if relevant. | By 5 June | Not started
Prints | 6 | Cellophane sleeves & backing boards | Protects prints; lets buyers handle them safely. | By 22 May | Not started | 80
Prints | 7 | Print storage / browse box | Hinged box or wire rack so customers can flip through. | By 1 June | Not started | 50
Prints | 8 | Tubes for sold rolled prints | A few in each common size for transport. | By 1 June | Not started | 20
Stall & Display | 1 | Confirm stall pitch & dimensions | Get exact measurements from organisers; indoor vs outdoor; power? | ASAP | Not started
Stall & Display | 2 | Backdrop / display walls | Mesh panels, freestanding walls or pegboard; weight base for outdoor. | By 1 June | Not started | 250
Stall & Display | 3 | Easels & plinths for headline pieces | 1–2 hero pieces at eye level; everything else evenly hung. | By 1 June | Not started | 100
Stall & Display | 4 | Lighting | Battery-powered LED spots if no mains; warm white ~3000K. | By 1 June | Not started | 80
Stall & Display | 5 | Tablecloth / drape | Neutral linen; long enough to hide storage underneath. | By 1 June | Not started | 40
Stall & Display | 6 | Banner / sign with name & series title | Readable from 10m. Match website branding. | By 1 June | Not started | 60
Stall & Display | 7 | Artwork labels | Title, year, medium, dimensions, price. Consistent template. | By 5 June | Not started | 10
Stall & Display | 8 | Chair / stool | Comfort over a long day. | By 5 June | Not started
Stall & Display | 9 | Weights / sandbags (if outdoor) | Critical in wind; festivals are exposed. | By 5 June | Not started | 30
Pricing & Sales Kit | 1 | Card reader | SumUp / Square / Zettle. Charged + spare battery pack. | By 1 June | Not started | 30
Pricing & Sales Kit | 2 | Cash float | £100 in mixed change. | Day before | Not started | 100
Pricing & Sales Kit | 3 | Inventory & sales tracker | One-page sheet; tick when sold; reconcile each evening. | By 5 June | Not started
Pricing & Sales Kit | 4 | Receipt book | Paper backup if card reader fails. | By 5 June | Not started | 5
Pricing & Sales Kit | 5 | Wrapping kit | Tissue, branded tape, paper bags, ribbon. | By 5 June | Not started | 40
Pricing & Sales Kit | 6 | Provenance / certificate cards | For sold originals & limited prints. | By 1 June | Not started | 15
Marketing & Promotion | 1 | Business cards | Match website; QR to portfolio. Order with buffer time. | By 15 May | Not started | 40
Marketing & Promotion | 2 | Postcards of headline works | Free giveaway — keeps you in mind after the show. | By 22 May | Not started | 60
Marketing & Promotion | 3 | Mailing list signup | Clipboard with sheet OR QR code to a form. GDPR-compliant wording. | By 1 June | Not started
Marketing & Promotion | 4 | QR code to portfolio website | Print large; visible on stall; test it actually scans. | By 1 June | Not started
Marketing & Promotion | 5 | Social media announcement plan | Teaser posts T-4w, T-2w, T-1w, day-before, on-the-day. | By 10 May | Not started
Marketing & Promotion | 6 | Local press / newsletter outreach | Shrewsbury & Wiltshire local papers; festival's own programme. | By 8 May | Not started
Marketing & Promotion | 7 | Domain & website final pass | Live domain (not placeholder); contact form working; mobile checked. | By 15 May | Not started | 30
Logistics & Transport | 1 | Pay stall fee / confirm booking | Confirm in writing; keep receipt. | ASAP | Not started
Logistics & Transport | 2 | Vehicle plan | Will paintings + stall fit in your car? Hire van if not. | By 15 May | Not started
Logistics & Transport | 3 | Packing materials | Foam corners, blankets, bubble wrap, glassine for prints. | By 1 June | Not started | 50
Logistics & Transport | 4 | Transit / public liability insurance | Many festivals require £5m PLI; check policy covers transit & stall. | By 15 May | Not started | 120
Logistics & Transport | 5 | Set-up / breakdown timings | Get exact slot; arrive early on day 1. | ASAP | Not started
Logistics & Transport | 6 | Accommodation | If multi-day; book early — festival weekends sell out. | By 5 May | Not started | 250
Logistics & Transport | 7 | Site map & vehicle pass | Print + save offline on phone; rural signal can be patchy. | By 5 June | Not started
On-the-Day Kit | 1 | Toolbox | Hammer, picture hooks, gaffer tape, scissors, string, zip ties, screwdriver. | By 5 June | Not started
On-the-Day Kit | 2 | First aid + plasters | Hanging things will eventually nick a finger. | By 5 June | Not started | 10
On-the-Day Kit | 3 | Notebook & pens | For commission enquiries, contacts, ideas. | By 5 June | Not started
On-the-Day Kit | 4 | Phone charger + battery pack | Card reader + photos = phone dies fast. | By 5 June | Not started | 25
On-the-Day Kit | 5 | Lockable cash box | Small but sturdy; under the table. | By 5 June | Not started | 20
On-the-Day Kit | 6 | Weather kit | Sunscreen, hat, water bottle, layers, waterproof. June can be all four seasons. | By 5 June | Not started | 20
On-the-Day Kit | 7 | Food / snacks | Easy to eat one-handed while talking to a customer. | Day before | Not started | 15
Post-Show | 1 | Photograph the stall | For website / next application. Take before customers arrive. | Show day AM | Not started
Post-Show | 2 | Reconcile sales & stock | Same evening, while memory is fresh. | Show day PM | Not started
Post-Show | 3 | Email mailing list | Thank attendees; offer a small post-show print discount. | Within 1 wk | Not started
Post-Show | 4 | Thank-yous to organisers / press | Builds the relationship for next year. | Within 1 wk | Not started
Post-Show | 5 | Lessons learned doc | What sold, what didn't, what to change for next show. | Within 2 wks | Not started
[5 empty] | TOTAL EST. COST | 2930
|  | Progress: | 0 of 62 done